## Sheet1
Stream | Subsub Header | Milestone (Y/N) | Numbering | Owner | Timeline | New timeline | Status | Comments
License and Permit Build | Engineering Partner Onboarded | Milestone | 1 | Tahera | 30th April, 2026 | 25th May, 2026
| Contract Signing Completed | Task | 1.1 | Tahera |  | 22nd June, 2026
| Prototype and HLD ready and signed off by Product and Tech Exports | Milestone | 2 | Tahera, Ghanshyam
| Persona App Prototypes Completed and Signed Off | Task | 2.1 | Sanjana | 30th April, 2026 | 23rd June, 2026
| Prototype Reviewed by Product Team (Subham, Andrew, Megha) | Task | 2.11 | Sanjana |  | 23rd June, 2026
| Prototype Reviewed by Jojo and Feedback Incorporated | Task | 2.12 | Sanjana |  | 23rd June, 2026
| Prototype Reviewed by Karthikeyan | Task | 2.13 | Sanjana |  | 17th June, 2026
| KK to review dashboard | Task | 2.14 | Tahera |  | 23rd June, 2026
| Prototype of Internal Telemetry Dashboard | Task | 2.15 | Sanjana |  | 23rd June, 2026
| PRD Completed and Signed off | Task | 2.2 | Tahera
| Identify out of the box integrations - Payments, SMS, Email | Task | 2,21 | Tahera |  | 30th June, 2026
| PRD - Overall | Task | 2.22 | Tahera |  | 15th June, 2026
| PRD - Modules 1-7 | Task | 2.23 | Tahera |  | 25th June, 2026
| PRD - 8 - 15 | Task | 2.24 | Tahera |  | 30th June, 2026
| Roadmap Created | Task | 2.25 | Tahera + Ghanshyam |  | 18th June, 2026
| HLD Created and Signed Off | Task | 3.2 | Ghanshyam |  | 15th June, 2026
| HLD Presented in Tech Council | Task | 3.21 | Ghanshyam |  | 21th June, 2026
| All platform Saasification changes required for SaaS completed and PR merged | Milestone | 4 | Ghanshyam | 31st May, 2026 | 24th May, 2026
| Sprint Plan Created | Task | 4.1 | Es Magico |  | 23rd June, 2026
| Trade License as a template is available and configurable to 1 country use case | Milestone | 5 | Ghanshyam | 31st May, 2026 | 31st July, 2026
| Partner can create an account and go live with a License template in 1 week (no payment adaptor) | Milestone | 6 | Ghanshyam | 31st May, 2026 | 10th August, 2026
| L&P SaaS Version Ready - deployed either on Production instance or Sandbox | Milestone | 7 | Ghanshyam | 31st June, 2026 | 15th August, 2026
| WCAG AA for LnP SaaS Audit Complete and Compliance changes done | Milestone | 8 | Tahera + Es Magico | 31st June, 2026 | 30th August, 2026
License and Permit PLG Lifecycle | Webpage and V1 version of pitch deck for LnP SaaS ready for external conversations | Milestone | 9 | Tahera
| Create Plan on making noise | N |  | Tahera |  | 15th June, 2026
| Webpage Created | Task | 9.1 | Tahera |  | 8th June, 2026
| Website Reviewed and Signed off | Task | 9.2 | Tahera |  | TBD
| Deck ready for review | Task | 9.3 | Tahera |  | 24th May, 2026
| Deck reviewed and signed off by Jojo | Task | 9.4 | Tahera
| Multiple options for Infra Costing created for Partner | N |  | Ghanshyam |  | 16th June, 2026
Internal Operations | Reporting Metrics finalized | N |  | Tahera |  | 16th June, 2026
| Internal Reporting Website Created | N |  | Tahera |  | 16th June, 2026
| Video | N |  | Tahera
| Discussion on whether we should call it SaaS or not | N |  | Tahera
| Webinar with XYZ |  |  | Tahera
| Forums to plant this in |  |  | Tahera

## Sheet2
We will have haed winds against anchoring too heavily on SaaS in this environment
As is going to kill SaaS vs AI is going to Strengthen SaaS
Do you want to use a new term?
Arrive at a term
| Sprint Showcase |  | Sprint End
| Design Sprint |  | 19th June
Deliverables | Prototype | Citizen, Employee, Service Owner
| Tech Design | Swagger
Key Decisions
- UI
- Dashboard (In progresS)
Value proposition Deck